## Sheet1
Work Item Type | Title | State | Estimate
Epic | Wildlife Observation Recording | New
User Story | Record wildlife observation | New | 5
Task | Implement observation input form | New | 3
Task | Add geolocation capture | New | 2
Task | Support photo/video upload | New | 3
User Story | Sync offline observations | New | 3
Task | Implement sync queue | New | 2
Epic | IoT Device Data Integration | New
User Story | Ingest real‑time telemetry | New | 8
Task | Implement IoT ingestion API | New | 3
Task | Parse GPS/motion data | New | 3
User Story | Display live & historical data | New | 5
Task | Build device detail screen | New | 3
Epic | Real‑Time Animal Movement Monitoring | New
User Story | Visualize animal movement | New | 8
Task | Implement heatmap | New | 3
Task | Implement movement trails | New | 3
User Story | Trigger movement alerts | New | 5
Task | Define alert rules | New | 2
Epic | IoT Device Deployment & Maintenance | New
User Story | Register & deploy IoT devices | New | 5
Task | Device registration form | New | 2
Task | Deployment workflow | New | 3
User Story | Track device health | New | 5
Task | Device health dashboard | New | 3
Epic | Patrol Scheduling & Task Management | New
User Story | Create patrol tasks | New | 5
Task | Patrol task creation UI | New | 2
Task | Assignment workflow | New